## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | TO-DO LIST APP
Enter Company Name in cell B2. A legend is in cells I2 through AC2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Leader: Lưu Thành Đạt
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3.
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart. | [8 empty] | Tháng 9 | [21 empty] | Tháng 10 | [30 empty] | Tháng 11 | [29 empty] | Tháng 12
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Functions | Category | Milestone | Assigned To | Story Point | Start | End | PERIODS | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule. | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [81 empty] | #REF! | #REF! | #REF! | #REF! | [13 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE PROJECT |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Project | Feature | Milestone_1 | Leader |  | 19/10/2020 | 27/10/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE SECTION |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Section | Feature | Milestone_1 | Leader |  | 19/10/2020 | 27/10/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE TASK |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Task | Feature | Milestone_1 | Hằng |  | 19/10/2020 | 27/10/2020
| Search | Feature | Milestone_1 | Chương |  | 23/10/2020 | 30/10/2020
| Sort by | Feature | Milestone_1 | Nhữ Hào |  | 23/10/2020 | 30/10/2020
| Group by | Feature | Milestone_1 | Leader |  | 23/10/2020 | 30/10/2020
| Favorite management | Feature | Milestone_1 | Chương |  | 25/10/2020 | 2020-03-11
| Rich Text | Feature | Milestone_1 | Bôn |  | 25/10/2020 | 2020-03-11
| Set priority | Feature | Milestone_1 | Nhữ Hào |  | 25/10/2020 | 2020-03-11
| Set Tag | Feature | Milestone_1 | Leader |  | 25/10/2020 | 2020-03-11
| Add Website as Task | Feature | Milestone_1 | Leader |  | 25/10/2020 | 2020-03-11
| Copy & paste multiple lines | Feature | Milestone_1 | Giang |  | 25/10/2020 | 2020-03-11
| Filter Query | Feature | Milestone_1 | Khoa |  | 25/10/2020 | 2020-03-11
| Drag & Drop | Feature | Milestone_1 | Hằng |  | 25/10/2020 | 2020-03-11
| Undo Task | Feature | Milestone_1 | Thắng |  | 25/10/2020 | 2020-03-11
| Set Layout | Feature | Milestone_1 | Anh |  | 25/10/2020 | 2020-03-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE SUBTASK |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Subtask | Feature | Milestone_1 | Nhật Hào |  | 21/10/2020 | 27/10/2020
| POMODORO |  |  |  | 8 | 25/10/2020 | 2020-06-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set Time | Feature | Milestone_2 | Chương |  | 25/10/2020 | 2020-02-11
| Set Task | Feature | Milestone_2 | Bôn |  | 25/10/2020 | 2020-02-11
| Extend Time | Feature | Milestone_2 | Leader |  | 25/10/2020 | 2020-05-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Pause Pomodoro | Feature | Milestone_2 | Nhật Hào |  | 25/10/2020 | 2020-05-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Break Pomodoro | Feature | Milestone_2 | Bôn |  | 25/10/2020 | 2020-05-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Auto Change Task's Status | Feature | Milestone_2 | Chương |  | 27/10/2020 | 2020-05-11
| View History | Feature | Milestone_2 | Nhữ Hào |  | 27/10/2020 | 2020-06-11
Phân Tích Những Rủi Ro của Phần Mềm | Statistics | Feature | Milestone_2 | Leader |  | 30/10/2020 | 2020-06-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| REMINDER |  |  |  | 8 | 27/10/2020 | 2020-03-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set period of time | Feature | Milestone_3 | Chương |  | 27/10/2020 | 2020-01-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set point of time | Feature | Milestone_3 | Nhật Hào |  | 27/10/2020 | 2020-01-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Add Reminded Task | Feature | Milestone_3 | Chương |  | 27/10/2020 | 2020-01-11
Del Reminder | Delete Reminded Task | Feature | Milestone_3 | Hằng |  | 27/10/2020 | 2020-01-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set Nofications | Feature | Milestone_3 | Hằng |  | 29/10/2020 | 2020-02-11
| Set sending email option | Feature | Milestone_3 | Khoa |  | 29/10/2020 | 2020-02-11
| View Reminder List | Feature | Milestone_3 | Chương |  | 31/10/2020 | 2020-03-11
| View History | Feature | Milestone_3 | Nhật Hào |  | 31/10/2020 | 2020-03-11
| LOGIN & LOGOUT |  |  |  | 3 | 3/11/2020 | 5/11/2020
| Login with username / password | Feature | Milestone_3 | Leader |  | 3/11/2020 | 4/11/2020
| Login with Google Account | Feature | Milestone_3 | Leader |  | 3/11/2020 | 4/11/2020
| Forgot password | Feature | Milestone_3 | Leader |  | 3/11/2020 | 4/11/2020
Chia Các Branch Dev Trên Github | Change Google Account | Feature | Milestone_3 | Khoa |  | 4/11/2020 | 2020-05-11
| Logout | Feature | Milestone_3 | Chương |  | 3/11/2020 | 4/11/2020
| REPEATER |  |  |  | 5 | 06/11/2020 | 12/11/2020
| Set Task | Feature | Milestone_4 | Chương |  | 06/11/2020 | 09/11/2020
| Set Email option | Feature | Milestone_4 | Nhật Hào |  | 08/11/2020 | 12/11/2020
Phân Tích Các Chuẩn Dữ Liệu Của API | Set period of time | Feature | Milestone_4 | Hằng |  | 08/11/2020 | 09/11/2020
| Set point of time | Feature | Milestone_4 | Nhữ Hào |  | 09/11/2020 | 09/11/2020
| Set time loop | Feature | Milestone_4 | Bôn |  | 07/11/2020 | 10/11/2020
| View repeated task | Feature | Milestone_4 | Nhật Hào |  | 06/11/2020 | 12/11/2020
| Cancel repeater | Feature | Milestone_4 | Hằng |  | 06/11/2020 | 09/11/2020
| USER ACCOUNT MANAGEMENT (ADMIN) |  |  |  | 5 | 9/11/2020 | 12/11/2020
| C.R.U.D Account's Info | Feature | Milestone_4 | Chương |  | 9/11/2020 | 12/11/2020
This is an empty row | Block Account | Feature | Milestone_4 | Bôn |  | 9/11/2020 | 12/11/2020
| Unblock Account | Feature | Milestone_4 | Thắng |  | 9/11/2020 | 12/11/2020
| Delete Account | Feature | Milestone_4 | Hằng |  | 9/11/2020 | 12/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DEFAULT PROJECT MANAGEMENT |  |  |  | 5 | 11/11/2020 | 14/11/2020
| Inbox | Feature | Milestone_5 | Nhật Hào |  | 11/11/2020 | 12/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Today | Feature | Milestone_5 | Giang |  | 12/11/2020 | 13/11/2020
| Tomorrow | Feature | Milestone_5 | Giang |  | 13/11/2020 | 14/11/2020
| Week | Feature | Milestone_5 | Thắng |  | 13/11/2020 | 14/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Upcomming | Feature | Milestone_5 | Chương |  | 14/11/2020 | 14/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USER INFORMATION MANAGEMENT (USER) | USER INFORMATION MANAGEMENT (USER) |  |  |  | 3 | 15/11/2020 | 18/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Change Username | Feature | Milestone_5 | Leader |  | 15/11/2020 | 18/11/2020
| Change Password | Feature | Milestone_5 | Leader |  | 15/11/2020 | 18/11/2020
| Change Google Account | Feature | Milestone_5 | Hằng |  | 17/11/2020 | 18/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Change Name | Feature | Milestone_5 | Nhữ Hào |  | 15/11/2020 | 18/11/2020
| Change Location | Feature | Milestone_5 | Bôn |  | 15/11/2020 | 18/11/2020
| Change email | Feature | Milestone_5 | Nhữ Hào |  | 15/11/2020 | 18/11/2020
| SYSTEM NOTIFICATION MANAGEMENT |  |  |  | 5 | 21/11/2020 | 27/11/2020
| Add System Notification | Feature | Milestone_5 | Nhật Hào |  | 21/11/2020 | 23/11/2020
| View System Notification | Feature | Milestone_5 | Bôn |  | 21/11/2020 | 23/11/2020
| Set Time Sending | Feature | Milestone_5 | Nhữ Hào |  | 25/11/2020 | 27/11/2020
| Select User Zone | Feature | Milestone_5 | Bôn |  | 25/11/2020 | 27/11/2020
| Cancel System Notification | Feature | Milestone_5 | Chương |  | 21/11/2020 | 22/11/2020
| USER NOTIFICATION MANAGEMENT |  |  |  | 5 | 24/11/2020 | 27/11/2020
| View Notification | Feature | Milestone_6 | Nhật Hào |  | 24/11/2020 | 26/11/2020
| Seen Notication | Feature | Milestone_6 | Nhật Hào |  | 24/11/2020 | 26/11/2020
| Delete Notification | Feature | Milestone_6 | Chương |  | 24/11/2020 | 27/11/2020
| Setting Notification Options | Feature | Milestone_6 | Anh |  | 24/11/2020 | 27/11/2020
| EXPORT & PRINT | Feature |  |  | 8 | 29/11/2020 | 6/12/2020
| Export chart | Feature | Milestone_6 | Hằng |  | 29/11/2020 | 2/12/2020
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | Export achivement | Feature | Milestone_6 | Nhữ Hào |  | 29/11/2020 | 2/12/2020
| Export User Account | Feature | Milestone_6 | Nhật Hào |  | 29/11/2020 | 2/12/2020
| Export Statistics | Feature | Milestone_6 | Hằng |  | 29/11/2020 | 2/12/2020
| Export Completed Task | Feature | Milestone_6 | Leader |  | 29/11/2020 | 2/12/2020
| Print file pdf | Feature | Milestone_6 | Bôn |  | 2/12/2020 | 6/12/2020
| Print file image | Feature | Milestone_6 | Nhữ Hào |  | 2/12/2020 | 6/12/2020
| Export multiple files | Feature | Milestone_6 | Leader |  | 4/12/2020 | 6/12/2020
| STATISTICS |  |  |  | 8 | 7/12/2020 | 15/12/2020
| Completed Task Statistics | Feature | Milestone_7 | Leader |  | 7/12/2020 | 12/12/2020
| All Task Statistic | Feature | Milestone_7 | Leader |  | 7/12/2020 | 12/12/2020
| Tag Task Statistics | Feature | Milestone_7 | Chương |  | 7/12/2020 | 12/12/2020
| Deadline Task Statistics | Feature | Milestone_7 | Nhật Hào |  | 11/12/2020 | 15/12/2020
| Achievement Statistics | Feature | Milestone_7 | Nhật Hào |  | 11/12/2020 | 15/12/2020
| Pomodoro Statistics | Feature | Milestone_7 | Chương |  | 11/12/2020 | 15/12/2020
| Using App Statistics | Feature | Milestone_7 | Chương |  | 11/12/2020 | 15/12/2020
| MY CHART |  |  |  | 13 | 7/12/2020 | 14/12/2020
| Add Task | Feature | Milestone_7 | Leader |  | 7/12/2020 | 8/12/2020
| Move Task | Feature | Milestone_7 | Leader |  | 7/12/2020 | 8/12/2020
| Set Relationship | Feature | Milestone_7 | Leader |  | 9/12/2020 | 12/12/2020
| Change Status Task | Feature | Milestone_7 | Leader |  | 7/12/2020 | 7/12/2020
| Save Chart | Feature | Milestone_7 | Chương |  | 12/12/2020 | 14/12/2020
| View Chart List | Feature | Milestone_7 | Chương |  | 7/12/2020 | 8/12/2020
| Delete Chart | Feature | Milestone_7 | Chương |  | 7/12/2020 | 8/12/2020
ADD FRIENDS | ADD FRIENDS |  |  |  | 3 | 15/12/2020 | 19/12/2020
| Send Invitation | Feature | Milestone_8 | Nhữ Hào |  | 15/12/2020 | 16/12/2020
| Accept Invitation | Feature | Milestone_8 | Nhật Hào |  | 15/12/2020 | 17/12/2020
| View Friend List | Feature | Milestone_8 | Hằng |  | 15/12/2020 | 16/12/2020
| Share Achievement | Feature | Milestone_8 | Nhật Hào |  | 15/12/2020 | 18/12/2020
| Unfriend | Feature | Milestone_8 | Giang |  | 15/12/2020 | 19/12/2020
RANKING | RANKING |  |  |  | 3 | 17/12/2020 | 19/12/2020
| View ranking list (World) | Feature | Milestone_8 | Giang |  | 17/12/2020 | 18/12/2020
| View ranking list (Friend) | Feature | Milestone_8 | Chương |  | 17/12/2020 | 19/12/2020
| View Current Rank | Feature | Milestone_8 | Thắng |  | 17/12/2020 | 18/12/2020
| Increase Score | Feature | Milestone_8 | Anh |  | 17/12/2020 | 19/12/2020
ACHIEVEMENT | ACHIEVEMENT |  |  |  | 5 | 15/12/2020 | 19/12/2020
| View Achievement List | Feature | Milestone_8 | Chương |  | 15/12/2020 | 16/12/2020
| Record Achievement | Feature | Milestone_8 | Chương |  | 15/12/2020 | 17/12/2020
| Get Score | Feature | Milestone_8 | Hằng |  | 17/12/2020 | 18/12/2020
| Share Achievement | Feature | Milestone_8 | Hằng |  | 18/12/2020 | 19/12/2020
BUILDING SYSTEM | BUILDING SYSTEM |  |  |  | 20 | 07/12/2020 | 25/12/2020
| Create Your City | Feature | Milestone_9 | Leader |  | 07/12/2020 | 12/12/2020
| Buy Building | Feature | Milestone_9 | Leader |  | 07/12/2020 | 16/12/2020
| Sell Building | Feature | Milestone_9 | Leader |  | 12/12/2020 | 16/12/2020
| Move Building | Feature | Milestone_9 | Khoa |  | 14/12/2020 | 17/12/2020
| Share Your City | Feature | Milestone_9 | Hằng |  | 16/12/2020 | 18/12/2020
| Unclock new building | Feature | Milestone_9 | Leader |  | 18/12/2020 | 25/12/2020
MY MUSIC | MY MUSIC |  |  |  | 5 | 21/12/2020 | 24/12/2020
| Choose music | Feature | Milestone_9 | Nhữ Hào |  | 21/12/2020 | 22/12/2020
| Upload your music | Feature | Milestone_9 | Giang |  | 21/12/2020 | 24/12/2020
| Pause music | Feature | Milestone_9
| Continues music | Feature | Milestone_9
| Break music | Feature | Milestone_9